## 1
WATER AND SANITATION AGENCY, FDA, FAISALABAD.
FORMULATION OF ANNUAL DEVELOPMENT PROGRAMME 2018-19 & MTDF 2019-2021.
[23 empty] | (Rs. in millions) |  | ANNEX-I
S # | Project Code (Lo No.) |  | Old G.S No. 2017-18 | Name of Scheme | District | Tehsil | Consultancy / PP # | Approval/ Revision Date. | Approved/ Estimated Cost |  |  | Major Component | Major Targets (2018-2019) | Exp. Upto June 2018 | (ADP 2018-19 Proposed) | [6 empty] | Projection for 2019-2020 | Projection for 2020-2021 | Throw for-ward beyond June, 2021 | Remarks
| Cap. | Rev. | [6 empty] | Local | Foreign Aid | Total |  |  |  | Local |  | F/Aid |  | Total |  | Grand Total Rev. + Capital
[15 empty] | Capital | Revenue | Capital | Revenue | Capital | Revenue
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
A: On Going Schemes
1 |  |  | 8813 | Extension of water Resource Faisalabad for city Phase-II (French Funded) | Fsd. | Faisalabad | Whole city | Approved | 2846.515 | 11790.413 | 14636.928 | Extension of existing Water Treatment Plant 10 mgd. 1 No. New Water Treatment Plant 20mgd. 1 No. Installation of distrib- ution mains 100mm 15.6No. Purchase of land. 350 acre | Purchase of land. 350 acre. | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Scheme approved by ECNEC on 24-11-2018. A.A. issued on 29-12-2017. Release of funds is awaited.
2 | LO15001993 |  | 8814 | Construction of Disposal Station at Dawood Chowk. | Fsd. | Faisalabad | 68 | Approved by DDWP on 31-07-2015. A.A issued on 24-08-2015. | 80 | - | 80 | i. Pumping Station along- with pumping machinery. 1 No. | Civil works of pumping station. | 34.161 | 45.839 | 0 | 0 | 0 | 45.839 | 0 | 45.839 | 0 | 0 | 0 | Work in progress. | #REF!
3 | LO15001991 |  | 8816 | Extension of water supply distribution network to unserved areas. | Fsd. | Faisalabad | Whole city | Approved by PDWP on 20-10-2015 A.A. issued on 19/11/2015. | 548.5 | - | 548.5 | Water supply network 3" to 16" dia. Construction of Overhead & ground storage. Pumping machinery. | Construction of ground storage & pumping machinery. Water supply network | 375 | 173.5 | 0 | 0 | 0 | 173.5 | 0 | 173.5 | 0 | 0 | 0 | Work in progress.
4 |  |  | 3110 | Laying of Sewerage Line Dia 9,12,15 in Usman Town, Usman Park, Dar-ul-Ihsan Town, Hussainabad, Rehman Colony, Chirag Town, Babar Colony, Tariq Colony, Jaggo Town, Aagha Town, Sajad Town, Bilawal Town, Khalid Colony etc. (Laying of Sewer Line 9”,12”,15” in Babar Colony, Amir Colony, Sher Singh Wala, Rafiq Colony, Bilawal Town, New Garden Town, Ali Garden, Ansari Colony, Chiragh Town, Sajjad Town, Muneeb Town, Babar Colony No. 2, Wali Pura, Khalid Colony) | Fsd. | Faisalabad | NA-85 | Approved by DDC on 30-08-2017. A.A issued on 31-08-2017. | 49.988 |  | 49.988 | P/L of Sewer Lines 9” dia to 12” dia. 11.62km | P/L of Sewer Lines 9” dia to 12” dia. 11.62km | 20 | 29.988 | 0 | 0 | 0 | 29.988 | 0 | 29.988 | 0 | 0 | 0 | Work in progress.
5 |  |  | 3149 | Provision of New Sewerage Network for Sewer Deficient Areas/Replacement of Existing Sewer Lines and Provision of Water Supply Lines, District Faisalabad. | Fsd. | Faisalabad | NA-83 | Approved by DDWP on 20-09-2017. A.A issued on 14-11-2017. | 99.8 |  | 99.8 | P/L of Sewer Lines 9” dia to 18” dia. 19.85km | P/L of Sewer Lines 9” dia to 18” dia. 19.85km | 30 | 69.8 | 0 | 0 | 0 | 69.8 | 0 | 69.8 | 0 | 0 | 0 | Work in progress.
6 | LO17011182 |  | 3150 | Provision/ Construction of Water Supply Lines in District Faisalabad | Fsd. | Faisalabad | PP-70 | Approved by DDC on 16-08-2017. A.A issued on 29-08-2017. | 24.988 |  | 24.988 | P/L of water supply lines 3” dia to 12” dia. 11.44km | P/L of water supply lines 3” dia to 12” dia. 8 km | 10 | 14.988 | 0 | 0 | 0 | 14.988 | 0 | 14.988 | 0 | 0 | 0 | Work in progress.
7 |  |  | 3152 | Provision of Funds for Sewerage and Water Supply Scheme Un-served Areas, NA-85, Faisalabad. | Fsd. | Faisalabad | NA-85 | Approved by DDWP on 20-09-2017. A.A issued on 21-10-2017. | 59.99 |  | 59.99 | P/L of Sewer Lines 9” dia to 18” dia. 13.36km | P/L of Sewer Lines 9” dia to 18” dia. 13.36km | 25 | 34.99 | 0 | 0 | 0 | 34.99 | 0 | 34.99 | 0 | 0 | 0 | Work in progress.
8 | LO17011183 |  | 3153 | Laying of Water Supply lines in Different Area in PP-71 | Fsd. | Faisalabad | PP-71 | Approved by DDC on 16-08-2017. A.A issued on 29-08-2017. | 19.97 |  | 19.97 | P/L of water supply lines 3” dia to 12” dia. 9.67km | P/L of Water Supply Lines 3” dia to 12” dia. 9.67km | 7.5 | 12.47 | 0 | 0 | 0 | 12.47 | 0 | 12.47 | 0 | 0 | 0 | Work in progress.
9 | LO17011184 |  | 3160 | Construction of providing and laying sewer line in NA-84. | Fsd. | Faisalabad | NA-84 | Approved by DDC on 16-08-2017. A.A issued on 29-08-2017. | 49.935 |  | 49.935 | P/L of Sewer Lines 9” dia to 12” dia. 12.10km | P/L of Sewer Lines 9” dia to 12” dia. 12.10km | 20 | 29.935 | 0 | 0 | 0 | 29.935 | 0 | 29.935 | 0 | 0 | 0 | Work in progress.
10 | LO17011061 |  | 3161 | Construction / Replacement of sewerage lines in District, Faisalabad. | Fsd. | Faisalabad | PP-70 | Approved by DDWP on 07-08-2017. A.A issued on 14-10-2017. | 74.998 |  | 74.998 | P/L of Sewer Lines 9” dia to 18” dia. 12.58km | P/L of Sewer Lines 9” dia to 18” dia. 12.58km | 30 | 44.998 | 0 | 0 | 0 | 44.998 | 0 | 44.998 | 0 | 0 | 0 | Work in progress.
11 | LO17011185 |  | 3162 | Provision of sewerage at Mohallah Neghayban pura (No.2), B-Block District Faisalabad | Fsd. | Faisalabad | PP-66 | Approved by DDC on 16-08-2017. A.A issued on 29-08-2017. | 2.492 |  | 2.492 | P/L of Sewer Lines 9” dia. 0.65km | P/L of Sewer Lines 9” dia. 0.65km | 2.5 | -0.008 | 0 | 0 | 0 | -0.008 | 0 | -0.008 | 0 | 0 | 0 | Work in progress.
12 |  |  | 7596 | Providing and Laying of Sewer and Water Supply Lines in different areas of PP-69, Faisalabad. | Fsd. | Faisalabad | PP-69 | Approved by DDC on 16-08-2017. A.A issued on 29-08-2017. | 10 |  | 10 | P/L of Sewer Lines in 9” dia to 12” dia. 2.57km | P/L of Sewer Lines in 9” dia to 12” dia. 2.57km | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work in progress.
13 |  |  | 8928 | Construction of Waste Water Treatment Plant in Faisalabad. | Fsd. | Faisalabad | NA-80 | Un-Approved | 14500 |  | 14500 | Construction of Wastewater Treatment Plant. Purchase of Land. 269 acre Construction of boundary wall. | Construction of boundary wall. | - | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 8000 | 6400 | 0 | Work in progress.
14 | LO17001202 |  | 8929 | Augmentation of Water Treatment Plant at Millat Town, Faisalabad. | Fsd. | Faisalabad | NA-82 | Approved by DDWP on 07-08-2017. A.A issued on 14-10-2017. | 99.94 |  | 99.94 | Construction of filter beds. 1 No. Construction of GSTs 3 Nos. | Construction of filter beds. 1 No. Construction of GSTs. 3 Nos. | 50 | 49.94 | 0 | 0 | 0 | 49.94 | 0 | 49.94 | 0 | 0 | 0 | Work in progress.
|  |  |  | Total:- |  |  |  |  | 18467.116 | 11790.413 | 30257.529 |  |  | 664.161 | 606.44 | 0 | 0 | 0 | 606.44 | 0 | 606.44 | 8000 | 6400 | 0
B=New Proposed Schemes 2018-2019
1 |  |  |  | Construction of arterial main, Secondary and distribution Network in the areas in the Eastern Part of City. | Fsd. | Faisalabad | NA-82, 83, 84 | Unapproved | 4993 |  | 4993 | Primary arterial main 600 to 1200mm. 49 km Secondary and distribution main. 195km | Primary arterial main 600 to 1200mm. 5 km Secondary and distribution main. 50 km | - | 415 | 0 | 0 | 0 | 415 | 0 | 415 | 1550 | 1550 | 1478 | A scheme "Extension of Water Resources for Faisalabad City Phase-II is approved for Rs. 14636 million" by ECNEC for production of 30 mgd water. AFD Bank agreed for funding of this scheme. They appointed the consultant M/s Artelia French to revisit the feasibility study and project outcomes. The consultant pointed out that expansion of system is essential parallel to this project. Accordingly FWASA / Govt. of Punjab, made formal commitment for allocation of financial resources for network extension and detailed implementation of plan.
2 |  |  |  | Improvement of water supply system through rehabilitation of GSTs OHRs and Pipe Network etc. | Fsd. | Faisalabad | Whole city | Unapproved | 615 |  | 615 | Water supply Network 6" to 16" dia. 30 km Ground storage tank rehabilitation / construction. 10 Nos. OHR rehabilitation / construction. 8 Nos. | Water supply Network 6" to 16" dia. 3 km Ground storage tank rehabilitation / construction. 2 Nos. OHR rehabilitation / construction. 2 Nos. | - | 200 | 0 | 0 | 0 | 200 | 0 | 200 | 415 | 0 | 0 | i. To balance and improve the water pressure by addition of GSTs, OHRs and new loops of water supply network .
3 |  |  |  | Rehabilitation / replacement of Sewerage System in Faisalabad City. | Fsd. | Faisalabad | Whole City | Un approved | 280 | 0 | 280 | Replacement of sewer line 9" dia to 36" dia. 14 km Repair of existing manhole chambers. 300 No. Replacement of forcemain. 4 km | Replacement of sewer line 9" dia to 36" dia. 4 km Repair of existing manhole chambers. 50 No. Replacement of forcemain. 2 km | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 180 | 0 | 0 | Some sewer lines have completed their useful life. Subsequently complaints of crown failures are increasing day by day. Residents of areas are agitating for replacement of these sewer lines. Replacement of these sewer lines is most essential to improve the service delivery upto satisfaction of consumers.
4 |  |  |  | P/L Trunk sewer from Elahi Abad pump station to pump station # 36, Faisalabad. | Fsd. | Faisalabad | 68, 69 | Un approved | 680 |  | 680 | Trunk Sewer 48" to 72" dia. 8.2 km Branch sewer 9" to 18" dia. 22 km Pumping Station along- with pumping machinery. 1 No. | Trunk Sewer 48" to 72" dia. 0.5 km Branch sewer 9" to 18" dia. 3 km |  | 80 | 0 | 0 | 0 | 80 | 0 | 80 | 300 | 300 | 0 | This was a part of updated Master Plan 1993-18 Phase-II but could not be implemented. This scheme was proposed in MTDF 2015-18 but unfortunately could not take place in ADP. Wastewater of Elahiabad disposal station is being pumped out into storm water channel No. 4 which is running in thickly populated areas. There are major environmental and sanitation issues as pumping station could not fully utilized to avoid the overflow of channel which can cause to loss to public property. On completion of this scheme, size of channel No. 4 will be reduced and free from wastewater & only be used for storm water.
5 |  |  |  | Construction of trunk sewer for 229/RB Makkuana, Central / Borstal jail area, 215/RB, 209/RB & adjoining areas of Eastern part of Faisalabad City. | Fsd. | Faisalabad | NA-80 PP-62 | Unapproved | 828 |  | 828 | Trunk Sewer 48" to 72" dia. 8.90km Branch sewer 9" to 24" dia 21.15 km Force main pumping station with machinery. 3 km Land acquisition. 1 acre | Trunk Sewer 48" to 72" dia. 1 km Branch sewer 9" to 24" dia. 2 km Land acquisition. 1 acre | - | 128 | 0 | 0 | 0 | 128 | 0 | 128 | 400 | 300 | 0 | A trunk sewer was proposed in updated Master Plan to cater the needs of the areas falling in the outskirts of the city especially along Jaranwala road, between Jaranwala road and Satiana road and Sheikhupura road. New abadies have developed in these localities but disposal of wastewater is not proper. Wastewater is accumulating in the open plots and streets. Health of residents of area is at risk. Prime Minister and Chief Minister offices have issued directives for submitting the scheme.
6 |  |  |  | Construction of force main from PS Gulistan colony No. 1 & PS-34, to divert the double stage to single stage pumping including rehabilitation of drain from Risalewala road to Dijkot seepage drain. | Fsd. | Faisalabad | 68, 69 | Un approved | 375 |  | 375 | Force main 1000mm. 5.1 km Force main 400mm. 3.10 km Drain rehabilitation. 6 km | Force main 1000mm. 5.1 km Drain rehabilitation. 6 km |  | 315 | 0 | 0 | 0 | 315 | 0 | 315 | 60 | 0 | 0 | There are different intermediate sewage pumping stations in the city which are pumping in the trunk sewers and again pumping at terminal point. Due to double stage pumping WASA has to bear the electricity bill and R&M of machinery twice. Both disposal stations falls at different FESCO feeders. When one feeder shuts down both pumping stations remain stopped. Wastewater overflows in upstream areas and suffer the service delivery. Now it is proposed to construct the forcemain to resolve the issue. Outlived drain needs to rehabilitate to cater the enhanced effluent.
7 |  |  |  | Provision of sewerage system for outskirts of the city area of Rasheed Abad, Nemat Abad, Ghatti, Bhaiwala Neitheri, Chak No. 225/R.B, etc Faisalabad. | Fsd. | Faisalabad | 85 PP-71, 72 | Un approved | 375 |  | 375 | Sewer line 9" to 18" dia. 60 km | Sewer line 9" to 18" dia. 16 km | - | 175 | 0 | 0 | 0 | 175 | 0 | 175 | 200 | 0 | 0 | The above mentioned areas were developed 20 to 30 years ago. Wastewater of these areas were used for cultivated lands through agriculture water courses. Now these cultivated agriculture land has converted into residential colonies. Trunk sewer has been laid in these areas and functional with huge investment. The outcomes of said investment can be fully utilized after laying the branch sewers. Accordingly scheme is proposed to serve the areas with sewerage system and improve the environmental conditions.
8 |  |  |  | Procurement of machinery for the disaster management plan. | Fsd. | Faisalabad | Whole City | Un approved | 300.55 | 0 | 300.55 | Water bowzer of 3000 gallon capacity. 5 No. Dewatering sets 2 cusec capacity. 8 No. Dewatering sets 3 cusec. capacity. 4 No. Dewatering sets 4 cusec. capacity. 4 No. Dumper Truck 8 ton capacity. 6 No. Excavator Short Boom 10 meter long. 1 No. Excavator long Boom 30 meter long. 1 No. | Water bowzer of 3000 gallon capacity. 5 No. Dewatering sets 2 cusec capacity. 8 No. Dewatering sets 3 cusec. capacity. 4 No. Dewatering sets 4 cusec. capacity. 4 No. Dumper Truck 8 ton capacity. 6 No. Excavator Short Boom 10 meter long. 1 No. Excavator long Boom 30 meter long. 1 No. | 0 | 300.55 | 0 | 0 | 0 | 300.55 | 0 | 300.55 | 0 | 0 | 0 | To provide the proper water supply and sanitation facility. The water bowzer and dewatering sets are proposed to be processed for heavy monsoon and in urban flood areas during earth quicks. This project is in line with SDG 6 clean water and sanitation.
9 |  |  |  | Rehabilitation / Remodeling of sludge carrier Satiana Road, Faisalabad. | Fsd. | Faisalabad | NA-83, 84 | Un approved | 480 |  | 480 | Conversion of katcha sullage carrier into pacca sullage carrier. 9.2 km | Conversion of katcha sullage carrier into pacca sullage carrier. 1.0 km | - | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 380 | 0 | 0 | A katcha sullage carrier was constructed in 2000 to cater the wastewater of Satiana road disposal station and pumping station No 31. Meanwhile a new sewage pumping station No. 46 has been constructed near Punjab Govt. Employees Housing Society and Outlet of disposal is also in this sullage carrier. Resultantly it became undersized. Furthermore area was opened and new housing schemes has been developed and some areas are under developing along Satiana road. It is urgent need to convert this katcha sullage carrier into pacca to avoid any incident and enhance the capacity according to requirement.
10 |  |  |  | Improvement of Civil structure for the existing Disposal stations. | Fsd. | Faisalabad | Whole city | Un approved | 200 |  | 200 | Pump House. 12 Nos. Screening chamber. 8 Nos. | Pump House. 6 Nos. Screening chamber. 2 Nos. |  | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 0 | Civil structure of different disposal stations were constructed before 1978, which require urgent rehabilitation. Due to toxic gases, these civil structures have considerably deteriorated and in a dangerous condition. Therefore, some machinery has shifted outside of these structures in open air. Due to which electric installation are suffering badly and a burden on WASA own source budget. It is essential to rehabilitate these civil structures to avoid any untoward incident.
11 |  |  |  | Extension & Rehabilitation of Waste Water Treatment Plant Chokera, Faisalabad. | Fsd. | Faisalabad | Eastern part of city | Un approved | 15000 |  | 15000 | Construction Wastewater Treatment Plant. 1 No. | Construction Wastewater Treatment Plant. 0.01 No. | - | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 6000 | 8900 | 0 | A wastewater treatment plant having capacity of 20 Mgd based on wastewater stabilization pond technology, exists in Faisalabad since long. At the same time its rehabilitation & further extension is required for which suitable land is already acquired. Capacity of this treatment plant needs to be enhenced from 20 mgd to 60 mgd. The untreated wastewater cause soil contamination along with envirnmental pollution resultantly unhygienic conditions for the public.
12 |  |  |  | Construction of Southern Wastewater Treatment Plant, Faisalabad. | Fsd. | Faisalabad | NA 81, NA 85 | Un Approved | 20000 |  | 20000 | Construction of Wastewater Treatment Plant. 1 No. Acquisition of Land. 1 Job. Trunk Sewer 54" to 120". 10 km | Acquisition of Land. 1 Job. | - | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 7900 | 12000 | 0 | A wastewater treatment plant is proposed in Updated Master Plan 1993 which is also proposed by JICA Consultants in their interim report of Master Plan study (2018-38), along with trunk sewer to cater the wastewater of lateral sewers & pumping stations on the western side of the city. The existing wastewater is being pumped out into Dijkot seepage drain which is ultimately dispose off into River Ravi. The untreated wastewater cause soil contamination along with envirnmental pollution resultantly unhygienic conditions for the public.
|  |  |  | Total B:- |  |  |  |  | 44126.55 | 0 | 44126.55 |  |  | 0 | 2113.55 | 0 | 0 | 0 | 2113.55 | 0 | 2113.55 | 17485 | 23050 | 1478
|  |  |  | Grand Total (A+B):- |  |  |  |  | 62593.666 | 11790.413 | 74384.079 |  |  | 664.161 | 2719.99 | 0 | 0 | 0 | 2719.99 | 0 | 2719.99 | 25485 | 29450 | 1478
Faisalabad is flat terrain and waste water is disposing off after two to three stage pumping which needs huge electricity & POL charges. Furthermore, these pumping stations fall on different electric feeders and electric shutdown programme is also varies, resultantly problems are increase day by day. It is required to convert to singe stage pumping to safe the revenue and improve the services delivery.

## one page
Annex-'I'
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
4993 | - | 415 |  | 415 | 1550 | - | 1550 | 1478
1 | Title of the Proposed Project |  |  |  | Construction of arterial main, Secondary and distribution Network in the areas in the Eastern Part of City.
2 | Proponent Information |  |  |  | Primary arterial main 600 to 1200mm |  |  | 49 km
[5 empty] | Secondary and distribution main |  |  | 195 km
3 | Goals & Objectives set to be achieved. |  |  |  | A scheme "Extension of Water Resources for Faisalabad City Phase-II is approved for Rs. 14636 million" by ECNEC for production of 30 mgd water. AFD Bank agreed for funding of this scheme. They appointed the consultant M/s Artelia French to revisit the feasibility study and project outcomes. The consultant pointed out that expansion of system is essential parallel to this project. Accordingly FWASA / Govt. of Punjab, made formal commitment for allocation of financial resources for network extension and detailed implementation of plan.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil).
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | Yes
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | To improve the services delivery
8 | Nearest place where similar facility is available. |  |  |  | It is enhancement of capacity of existing treatment plant.
9 | Gestation Period |  |  |  | 4 Years
10 | Financial Phasing |  |  |  | As above
11 | Detail of post completion annual operation and maintenance cost (AOM&R) |  |  |  | -
| - Maintenance |  |  |  | Own source
| - HR |  |  |  | N,A
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | N.A
| - Other |  |  |  | N.A
12 | Beneficiaries (Type & Number) |  |  |  | 0.3 million.
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | 78.6 million / annum.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
615 |  | 200 |  | 200 | 415 | - | -
1 | Title of the Proposed Project |  |  |  | Improvement of water supply system through rehabilitation of GSTs OHRs and Pipe Network etc.
2 | Proponent Information |  |  |  | Water supply Network 6" to 16" dia |  |  | 30 km
[5 empty] | Ground storage tank rehabilitation / construction |  |  | 10 Nos.
[5 empty] | OHR rehabilitation / construction |  |  | 8 No.
3 | Goals & Objectives set to be achieved. |  |  |  | To balance and improve the water pressure by addition of GSTs, OHRs and new loops of water supply network .
To enhance the storage of water
The proposed scheme is in line with the SDG 6.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil). |  |  |  | Whole City.
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | Yes.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | N.A
8 | Nearest place where similar facility is available. |  |  |  | N.A
9 | Gestation Period |  |  |  | 2 Years
10 | Financial Phasing |  |  |  | As above.
11 | Detail of post completion annual operation and maintenance cost (AOM&R)
| - Maintenance |  |  |  | -
| - HR |  |  |  | -
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | -
| - Other |  |  |  | -
12 | Beneficiaries (Type & Number) |  |  |  | Existing consumers will be benefited.
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Existing consumers will be benefited.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
280 |  | 100 |  | 100 | 180 | - | - | -
1 | Title of the Proposed Project |  |  |  | Rehabilitation / replacement of Sewerage System in Faisalabad City.
2 | Proponent Information
[5 empty] | Replacement of sewer line 9" dia to 36" dia. Rehabilitation of existing manhole chambers. Construction of forcemain. |  |  | 14.0 km 300 Nos. 4.0 km..
3 | Goals & Objectives set to be achieved. |  |  |  | Some sewer lines have completed their useful life. Subsequently complaints of crown failures are increasing day by day. Residents of areas are agitating for replacement of these sewer lines. Replacement of these sewer lines is most essential to improve the service delivery upto satisfaction of consumers.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil). |  |  |  | Whole City.
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | N.A
8 | Nearest place where similar facility is available. |  |  |  | N.A
9 | Gestation Period |  |  |  | 2 Years
10 | Financial Phasing |  |  |  | As above.
11 | Detail of post completion annual operation and maintenance cost (AOM&R)
| - Maintenance |  |  |  | Own source
| - HR |  |  |  | -
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | -
| - Other |  |  |  | -
12 | Beneficiaries (Type & Number) |  |  |  | Existing consumers will be benefited.
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Service delivery will be improved.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
680 |  | 80 |  | 80 | 300 | - | 300
1 | Title of the Proposed Project |  |  |  | P/L Trunk sewer from Elahi Abad pump station to pump station # 36, Faisalabad.
2 | Proponent Information |  |  |  | Trunk Sewer 48" to 72" dia. |  |  | 8.2 km
[5 empty] | Branch sewer 9" to 18" dia |  |  | 22 km
[5 empty] | Pumping Station along with pumping machinery. |  |  | 1 No.
3 | Goals & Objectives set to be achieved. |  |  |  | This was a part of updated Master Plan 1993-18 Phase-II but could not be implemented. This scheme was proposed in MTDF 2015-18 but unfortunately could not take place in ADP. Wastewater of Elahiabad disposal station is being pumped out into storm water channel No. 4 which is running in thickly populated areas. There are major environmental and sanitation issues as pumping station could not fully utilized to avoid the overflow of channel which can cause to loss to public property. On completion of this scheme, size of channel No. 4 will be reduced and free from wastewater & only be used for storm water.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil). |  |  |  | Whole City.
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | N.A
8 | Nearest place where similar facility is available. |  |  |  | N.A
9 | Gestation Period |  |  |  | 3 Years
10 | Financial Phasing |  |  |  | As above.
11 | Detail of post completion annual operation and maintenance cost (AOM&R)
| - Maintenance |  |  |  | -
| - HR |  |  |  | -
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | -
| - Other |  |  |  | -
12 | Beneficiaries (Type & Number) |  |  |  | Existing consumers will be benefited.
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Service delivery will be improved & extended.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foreign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
828 | - | 128 |  | 128 | 400 | - | 300 | -
1 | Title of the Proposed Project |  |  |  | Construction of trunk sewer for 229/RB Makkuana, Central / Borstal jail area, 215/RB, 209/RB & adjoining areas of Eastern part of Faisalabad City.
2 | Proponent Information |  |  |  | Trunk Sewer 48" to 72" dia. |  |  | 8.90 km
[5 empty] | Branch sewer 9" to 24" dia |  |  | 21.15 km
[5 empty] | Force main pumping station with machinery |  |  | 3 km
[5 empty] | Land acquisition. |  |  | 1 Acre
3 | Goals & Objectives set to be achieved. |  |  |  | A trunk sewer was proposed in updated Master Plan to cater the needs of the areas falling in the outskirts of the city especially along Jaranwala road, between Jaranwala road and Satiana road and Sheikhupura road. New abadies have developed in these localities but disposal of wastewater is not proper. Wastewater is accumulating in the open plots and streets. Health of residents of area is at risk. Prime Minister and Chief Minister offices have issued directives for submitting the scheme.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil).
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | To improve the services delivery
8 | Nearest place where similar facility is available. |  |  |  | It is enhancement of capacity of existing treatment plant.
9 | Gestation Period |  |  |  | 3 Years
10 | Financial Phasing |  |  |  | As above
11 | Detail of post completion annual operation and maintenance cost (AOM&R) |  |  |  | -
| - Maintenance |  |  |  | Own source
| - HR |  |  |  | N,A
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | N.A
| - Other |  |  |  | N.A
12 | Beneficiaries (Type & Number) |  |  |  | 0.2 million persons
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | 26.50 million / annum.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement √
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
375 | - | 315 |  | 315 | 60 | - | - | -
1 | Title of the Proposed Project |  |  |  | Construction of force main from PS Gulistan colony No. 1 & PS-34, to divert the double stage to single stage pumping including rehabilitation of drain from Risalewala road to Dijkot seepage drain.
2 | Proponent Information |  |  |  | Force main 1000mm |  |  | 5.1 km
[5 empty] | Force main 400mm |  |  | 3.10 km
[5 empty] | Drain rehabilitation |  |  | 6 km
3 | Goals & Objectives set to be achieved. |  |  |  | There are different intermediate sewage pumping stations in the city which are pumping in the trunk sewers and again pumping at terminal point. Due to double stage pumping WASA has to bear the electricity bill and R&M of machinery twice. Both disposal stations falls at different FESCO feeders. When one feeder shuts down both pumping stations remain stopped. Wastewater overflows in upstream areas and suffer the service delivery. Now it is proposed to construct the forcemain to resolve the issue. Outlived drain needs to rehabilitate to cater the enhanced effluent.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil).
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | To improve the services delivery
8 | Nearest place where similar facility is available. |  |  |  | N.A
9 | Gestation Period |  |  |  | 2 Years
10 | Financial Phasing |  |  |  | As above
11 | Detail of post completion annual operation and maintenance cost (AOM&R) |  |  |  | -
| - Maintenance |  |  |  | Own source
| - HR |  |  |  | N,A
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | N.A
| - Other |  |  |  | N.A
12 | Beneficiaries (Type & Number) |  |  |  | 0.1 million persons
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Service delivery will be improved
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
375 | - | 175 |  | 175 | 200 | - | - | -
1 | Title of the Proposed Project |  |  |  | Provision of sewerage system for outskirts of the city area of Rasheed Abad, Nemat Abad, Ghatti, Bhaiwala Neitheri, Chak No. 225/R.B, etc Faisalabad.
2 | Proponent Information |  |  |  | Sewer line 9" to 18" dia |  |  | 60 km
3 | Goals & Objectives set to be achieved. |  |  |  | The above mentioned areas were developed 20 to 30 years ago. Wastewater of these areas were used for cultivated lands through agriculture water courses. Now these cultivated agriculture land has converted into residential colonies. Trunk sewer has been laid in these areas and functional with huge investment. The outcomes of said investment can be fully utilized after laying the branch sewers. Accordingly scheme is proposed to serve the areas with sewerage system and improve the environmental conditions.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil).
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | To improve the services delivery
8 | Nearest place where similar facility is available. |  |  |  | Trunk sewers already laid & functional.
9 | Gestation Period |  |  |  | 2 Years
10 | Financial Phasing |  |  |  | As above
11 | Detail of post completion annual operation and maintenance cost (AOM&R) |  |  |  | -
| - Maintenance |  |  |  | Own source
| - HR |  |  |  | N,A
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | N.A
| - Other |  |  |  | N.A
12 | Beneficiaries (Type & Number) |  |  |  | 0.06 million persons
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | 9.85 million / annum.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
300.55 | - | 300.55 |  | 300.55 | 0 |  | - | -
1 | Title of the Proposed Project |  |  |  | Procurement of machinery for the disaster management plan.
2 | Proponent Information |  |  |  | Water bowzer of 3000 gallon capacity. |  |  | 5 No.
[5 empty] | Dewatering sets 2 cusec capacity. |  |  | 8 No.
[5 empty] | Dewatering sets 3 cusec capacity. |  |  | 4 No.
[5 empty] | Dewatering sets 4 cusec capacity. |  |  | 4 No.
[5 empty] | Dumper Truck 8 ton capacity. |  |  | 6 No.
[5 empty] | Excavator Short Boom 10 meter long. |  |  | 1 No.
[5 empty] | Excavator long Boom 30 meter long. |  |  | 1 No.
3 | Goals & Objectives set to be achieved. |  |  |  | To provide the proper water supply and sanitation facility. The water bowzer and dewatering sets are proposed to be processed for heavy monsoon and in urban flood areas during earth quicks. This project is in line with SDG 6 clean water and sanitation.
4 | Rationale for ADP Funding |  |  |  | Own source is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil). |  |  |  | Whole city including nearby towns.
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | To improve the services delivery
8 | Nearest place where similar facility is available. |  |  |  | N.A
9 | Gestation Period |  |  |  | 1 Year
10 | Financial Phasing |  |  |  | As above
11 | Detail of post completion annual operation and maintenance cost (AOM&R) |  |  |  | -
| - Maintenance |  |  |  | Own source
| - HR |  |  |  | -
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | -
| - Other |  |  |  | -
12 | Beneficiaries (Type & Number) |  |  |  | Existing consumers will be benefited
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Existing consumers will be benefited
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion ü | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
480 | - | 100 | - | 100 | 380 | - | - | -
1 | Title of the Proposed Project |  |  |  | Rehabilitation / Remodeling of sludge carrier Satiana Road, Faisalabad.
2 | Proponent Information |  |  |  | Conversion of katcha sullage carrier into pacca sullage carrier 9.2 km
A katcha sullage carrier was constructed in 2000 to cater the wastewater of Satiana road disposal station and pumping station No 31. Meanwhile a new sewage pumping station No. 46 has been constructed near Punjab Govt. Employees Housing Society and Outlet of disposal is also in this sullage carrier. Resultantly it became undersized. Furthermore area was opened and new housing schemes has been developed and some areas are under developing along Satiana road. It is urgent need to convert this katcha sullage carrier into pacca to avoid any incident and enhance the capacity according to requirement.
3 | Goals & Objectives set to be achieved. |  |  |  | Increase in carrying capacity & covering of Drain. This project is inline with SDG 6: Clean Water and Sanitation
4 | Rationale for ADP Funding |  |  |  | Funds required for the remodelling of channel.
5 | Geographical Coverage (For whole province or specific distric/tehsil). |  |  |  | Eastern part of the city
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The scheme has been proposed to safely dispose off domestic / industrial waste water as per master plan.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | N.A
8 | Nearest place where similar facility is available. |  |  |  | N.A
9 | Gestation Period |  |  |  | 2 Years
10 | Financial Phasing |  |  |  | 2 Years
11 | Detail of post completion annual operation and maintenance cost (AOM&R)
| - Maintenance |  |  |  | Own source
- HR
| - Operation |  |  |  | Own source
- Repairs
- Other
12 | Beneficiaries (Type & Number) |  |  |  | Existing consumers will be benefited.
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Service delivery will be improved.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
200 | - | 100 |  | 100 | 100 | - | - | -
1 | Title of the Proposed Project |  |  |  | Improvement of Civil structure for the existing Disposal stations.
2 | Proponent Information |  |  |  | Pump House |  |  | 12 Nos.
[5 empty] | Screening chamber |  |  | 8 Nos.
3 | Goals & Objectives set to be achieved. |  |  |  | Civil structure of different disposal stations were constructed before 1978, which require urgent rehabilitation. Due to toxic gases, these civil structures have considerably deteriorated and in a dangerous condition. Therefore, some machinery has shifted outside of these structures in open air. Due to which electric installation are suffering badly and a burden on WASA own source budget. It is essential to rehabilitate these civil structures to avoid any untoward incident.
4 | Rationale for ADP Funding
5 | Geographical Coverage (For whole province or specific distric/tehsil). |  |  |  | Whole city
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars.
8 | Nearest place where similar facility is available. |  |  |  | N.A
9 | Gestation Period |  |  |  | 2 Years
10 | Financial Phasing |  |  |  | As above
11 | Detail of post completion annual operation and maintenance cost (AOM&R) |  |  |  | -
| - Maintenance |  |  |  | -
| - HR |  |  |  | -
| - Operation |  |  |  | Own source
| - Repairs |  |  |  | -
| - Other |  |  |  | -
12 | Beneficiaries (Type & Number) |  |  |  | Existing consumer
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Better service delivery
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR | Employement
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
15000 | - | 100 |  | 100 | 6000 | - | 8900 | -
1 | Title of the Proposed Project |  |  |  | Extension & Rehabilitation of Waste Water Treatment Plant Chokera, Faisalabad.
2 | Proponent Information |  |  |  | Construction Wastewater Treatment Plant |  |  | 1 No.
3 | Goals & Objectives set to be achieved. |  |  |  | A wastewater treatment plant having capacity of 20 Mgd based on wastewater stabilization pond technology, exists in Faisalabad since long. At the same time its rehabilitation & further extension is required for which suitable land is already acquired. Capacity of this treatment plant needs to be enhenced from 20 mgd to 60 mgd. The untreated wastewater cause soil contamination along with envirnmental pollution resultantly unhygienic conditions for the public.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil).
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars.
8 | Nearest place where similar facility is available.
9 | Gestation Period |  |  |  | 3 Years
10 | Financial Phasing |  |  |  | As above
11 | Detail of post completion annual operation and maintenance cost (AOM&R) |  |  |  | -
| - Maintenance |  |  |  | -
| - HR |  |  |  | Yes
| - Operation |  |  |  | -
| - Repairs |  |  |  | N.A
| - Other |  |  |  | N.A
12 | Beneficiaries (Type & Number) |  |  |  | Existing western side of the city
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Environmental condition will be improved.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR ü | Employement ü
WATER AND SANITATION AGENCY, FAISALABAD
Project Concept form for new projects / Initiatives
Rs in millions
Cost |  | Allocation for 2018-19 |  |  | Throw Forward
Local | Foeign | Cap | Rev | Total | 2019-20 |  | 2020-21 | Beyond 2021-22
20000 | - | 100 |  | 100 | 7900 | - | 12000
1 | Title of the Proposed Project |  |  |  | Construction of Southern Wastewater Treatment Plant, Faisalabad.
2 | Proponent Information |  |  |  | Construction of Wastewater Treatment Plant |  |  | 1 No.
[5 empty] | Acquisition of Land |  |  | 1 Job
[5 empty] | Trunk Sewer 54" to 120" |  |  | 10 Km
3 | Goals & Objectives set to be achieved. |  |  |  | A wastewater treatment plant is proposed in Updated Master Plan 1993 which is also proposed by JICA Consultants in their interim report of Master Plan study (2018-38), along with trunk sewer to cater the wastewater of lateral sewers & pumping stations on the western side of the city. The existing wastewater is being pumped out into Dijkot seepage drain which is ultimately dispose off into River Ravi. The untreated wastewater cause soil contamination along with envirnmental pollution resultantly unhygienic conditions for the public.
4 | Rationale for ADP Funding |  |  |  | Own source budget is insufficient to execute the scheme.
5 | Geographical Coverage (For whole province or specific distric/tehsil). |  |  |  | Western side of the city.
6 | How the project aligned with Sector Plan / Growth Strategy |  |  |  | The project is in line with SDG 6.
7 | Relationship of the Project with growth objectives / Pillars. |  |  |  | Ground water will be saved from pollution and creates good environmental condition.
8 | Nearest place where similar facility is available.
9 | Gestation Period |  |  |  | 3 Years (after award of work)
10 | Financial Phasing |  |  |  | As above
11 | Detail of post completion annual operation and maintenance cost (AOM&R) |  |  |  | -
| - Maintenance |  |  |  | -
| - HR |  |  |  | Yes
| - Operation |  |  |  | -
| - Repairs |  |  |  | N.A
| - Other |  |  |  | N.A
12 | Beneficiaries (Type & Number) |  |  |  | Existing western side of the city
13 | Expected Output (Qualitative & Outcome Quantitative) |  |  |  | Environmental condition will be improved.
14 | Priority (Indicate High, Normal or Low) |  |  |  | Top
15 | Alighment with Growth Strategy, Punjab (PI.Tick the applicable areas) |  |  |  | PPP/Private sector facilitation | Energy | Infrastructure | Urban Development √
[5 empty] | Social Inclusion √ | Social Outcomes √ | Capacity Building / HR ü | Employement ü